Walchand College of Engineering, Sangli Department of Computer Science and Engineering Mini-Project-2 (7VSCS346) · Synopsis Build Plan LogStream — Real-Time Log Monitoring Dashboard Rameshwari Satpute (23510007) · Pooja Bhosale (23510012) · Aasiya Ankali (23510020) Guide: Mr. A.A. Urunkar · HOD: Dr. A.R. Surve · 2025-26

| Member 1 — Rameshwari DevOps & Log Pipeline Engineer | Member 2 — Pooja Backend & Real-Time Systems Engineer | Member 3 — Aasiya Frontend & UI Engineer |
| --- | --- | --- |

# 1.  Project Overview

LogStream is a real-time log monitoring and visualization system. It uses Promtail to scrape logs, Grafana Loki as the storage backend, a Node.js + Socket.io server for real-time broadcasting, and a React + Tailwind frontend for live visualization — all containerized with Docker Compose.

| Project Title | LogStream — Real-Time Log Monitoring Dashboard |
| --- | --- |
| Course | Mini-Project-2 (7VSCS346) · WCE Sangli · 2025-26 |
| Guide | Mr. A.A. Urunkar |
| HOD | Dr. A.R. Surve |
| Domain | DevOps · Cloud Monitoring · Real-Time Data Streaming · SRE |
| SDG Alignment | SDG 9 — Industry, Innovation and Infrastructure |
| Team | Rameshwari (23510007) · Pooja (23510012) · Aasiya (23510020) |

## 1.1  Problem Statement

Modern software systems run many applications simultaneously, each producing log files scattered across different servers. Searching through them wastes time and delays fixing critical issues. LogStream centralizes all logs into a single real-time dashboard so developers can spot errors instantly.

## 1.2  Five-Layer Architecture

- Dummy Applications  —  Node.js scripts writing JSON, syslog, and plain-text logs

- Promtail Agent  —  scrapes log files, attaches metadata labels, pushes to Loki via HTTP

- Grafana Loki  —  label-based log store, queried via REST API (LogQL)

- Node.js + Socket.io Backend  —  tails Loki, emits socket events to all connected clients

- React + Tailwind Frontend  —  1000-entry buffer, terminal-style live dashboard with filtering

## 1.3  Tech Stack

| Dummy Apps | Node.js — generates JSON, syslog, plain-text logs at random intervals |
| --- | --- |
| Log Scraping | Promtail — tails files, attaches labels, ships to Loki via HTTP push |
| Log Storage | Grafana Loki — metadata-only index; 10x more efficient than Elasticsearch |
| Backend | Node.js (Express) — queries Loki REST API, hosts Socket.io server |
| Real-Time | Socket.io — WebSocket broadcast from server to all browser clients |
| Frontend | React 18 + Tailwind CSS — terminal UI, live filtering, 1000-log buffer |
| Containers | Docker + Docker Compose — single docker compose up starts full stack |
| Query Language | LogQL — e.g. {app="auth"} ¦= "error" ¦ json |

Member 1 — Rameshwari Satpute (23510007) DevOps & Log Pipeline Engineer · Infrastructure & Observability

Rameshwari owns the infrastructure layer — the dummy apps that generate logs, Promtail that scrapes them, Loki that stores them, and the Docker environment that ties everything together. Her work must be ready and validated before Member 2 can write a single line of backend code.

## Core Responsibilities

- Create three dummy Node.js log-generating applications (JSON, syslog, plain-text formats)

- Configure Promtail scraping rules with label selectors for each app

- Set up Grafana Loki in Docker with retention, storage, and health check

- Manage shared Docker volumes between dummy apps and Promtail

- Validate end-to-end pipeline — confirm all 3 apps visible in Loki before handoff

- Write infra-notes.md documenting the LogQL queries Member 2 will need

## Task Breakdown

| #1.1 | Create three dummy log-generating Node.js applications |
| --- | --- |
| Why | The system needs realistic multi-format log sources. Three apps cover all formats used in production: structured JSON (most Node/Go services), syslog RFC 3164 (Linux system services), and plain text (legacy apps). These are also the 'Dummy Apps' deliverable listed in the synopsis. |
| How | Create apps/json-logger/index.js, apps/syslog-logger/index.js, apps/text-logger/index.js. Each app writes logs at random 200-800ms intervals. JSON logger writes {timestamp, level, message, appId} to stdout and to /logs/json-app.log. Syslog logger writes RFC 3164 format. Text logger writes plain text. Mount /logs as a Docker shared volume. |
| Files | apps/json-logger/index.js · apps/syslog-logger/index.js · apps/text-logger/index.js · docker-compose.yml |
| CRITICAL |  |

| #1.2 | Configure Promtail with scraping rules for all three apps |
| --- | --- |
| Why | Without correct Promtail config, logs never reach Loki and the entire backend is untestable. Getting labels right is critical — Member 2 queries by these labels in LogQL. |
| How | Edit config/promtail-config.yml. Add a scrape_config for each app pointing to /logs/<appname>.log. Assign labels: job=logstream, app=<appname>, env=development. Add a pipeline_stage that parses JSON fields from the JSON logger. Verify with: docker compose logs promtail — should show no scrape errors and 'files found' messages. |
| Files | config/promtail-config.yml |
| Needs | Task 1.1 — log files must exist |
| HIGH |  |

| #1.3 | Set up Grafana Loki service in Docker Compose |
| --- | --- |
| Why | Loki is the central log store. All scraped logs flow into it and all backend queries read from it. It must be running and healthy before any backend integration testing is possible. |
| How | Add grafana/loki:2.9.0 to docker-compose.yml. Mount config/loki-config.yml. Expose port 3100. Add a health check hitting GET /ready. Create config/loki-config.yml with auth_enabled: false, local filesystem storage, and retention_period: 168h. Verify: curl http://localhost:3100/ready should return 'ready'. |
| Files | docker-compose.yml · config/loki-config.yml |
| CRITICAL |  |

| #1.4 | Validate pipeline and document LogQL queries for Member 2 |
| --- | --- |
| Why | Before handing off, Rameshwari must confirm all logs reach Loki and document the exact queries Member 2 needs. This prevents integration delays caused by wrong query syntax or missing labels. |
| How | Query Loki directly: curl 'http://localhost:3100/loki/api/v1/query?query={job="logstream"}'. Confirm results for all 3 apps. Write docs/infra-notes.md with: the query for all logs, query filtered by app, query filtered by level (using JSON pipeline), and the tail WebSocket URL: ws://loki:3100/loki/api/v1/tail?query={job="logstream"}. |
| Files | docs/infra-notes.md (new) |
| Needs | Tasks 1.1, 1.2, 1.3 |
| HIGH |  |

Member 2 — Pooja Bhosale (23510012) Backend & Real-Time Systems Engineer · Server-side Logic & Streaming

Pooja owns the Node.js backend — the engine of the system. She queries Loki for history, maintains a persistent tail connection for new logs, and broadcasts everything to connected Socket.io clients in real time. Her server is the bridge between the storage layer and the browser.

## Core Responsibilities

- Build the Express.js backend server with structured route layout

- Integrate Loki HTTP API for historical log queries via LogQL

- Establish a persistent /loki/api/v1/tail WebSocket connection

- Implement Socket.io server and broadcast new-log events to all clients

- Add server-side filter event handling to reduce unnecessary broadcasts

- Build log download endpoint — export filtered logs as a .log file

## Task Breakdown

| #2.1 | Build Express + Socket.io server scaffold |
| --- | --- |
| Why | The entire backend is built on top of the Express + Socket.io foundation. Without this scaffold, nothing else can be integrated or tested. |
| How | Create backend/server.js. Initialise Express, create http.createServer, attach Socket.io with CORS config. Add GET /health and GET /api/logs routes (query params: app, level, limit). Start on PORT from .env (default 4000). Create backend/package.json listing: express, socket.io, axios, ws, dotenv. Add backend/.env.example with LOKI_URL=http://loki:3100 and PORT=4000. |
| Files | backend/server.js · backend/package.json · backend/.env.example |
| CRITICAL |  |

| #2.2 | Integrate Loki query API for historical logs |
| --- | --- |
| Why | On page load, the frontend requests recent logs before the live tail starts. This requires querying Loki's range query endpoint using LogQL — the syntax Member 1 documented in infra-notes.md. |
| How | Create backend/services/lokiService.js. Write queryLogs(app, level, limit) that builds a LogQL expression, calls Loki's /loki/api/v1/query_range via axios, and returns a flat array of {id, timestamp, level, message, app, raw}. Parse the nested Loki response format (result[].stream, result[].values[]). Wire it to the GET /api/logs route in server.js. |
| Files | backend/services/lokiService.js (new) · backend/server.js |
| Needs | Task 2.1 + Member 1's Loki must be running and passing health check |
| CRITICAL |  |

| #2.3 | Implement Loki tail connection and Socket.io broadcast |
| --- | --- |
| Why | This is the core feature of the whole project. When a new log enters Loki, the backend receives it via the tail WebSocket and immediately emits it to all browser clients — creating the live stream. |
| How | In lokiService.js, add setupTail(onLog) that opens a WebSocket to ws://loki:3100/loki/api/v1/tail?query={job="logstream"}. Parse each incoming message (Loki tail response format) and call onLog(entry) for each log line. In server.js, call setupTail and inside onLog call io.emit('new-log', entry). Add reconnect logic: on WS close, reconnect after 2000ms. |
| Files | backend/services/lokiService.js · backend/server.js |
| Needs | Task 2.2 must be working |
| CRITICAL |  |

| #2.4 | Log download endpoint |
| --- | --- |
| Why | The synopsis use-case diagram explicitly includes 'Download Logs' as a primary use case. This endpoint exports whatever the user is currently viewing as a downloadable .log file. |
| How | Add GET /api/logs/download to server.js. Accept same filter params as /api/logs. Query Loki, format each entry as 'timestamp LEVEL [app] message\n'. Set response headers: Content-Type: text/plain, Content-Disposition: attachment; filename=logstream-export.log. Stream the formatted lines to the response. |
| Files | backend/server.js |
| Needs | HIGH |
| 0D9488 |  |

| #2.5 | Socket.io client filter event |
| --- | --- |
| Why | Without server-side filtering, the server broadcasts every log to every client regardless of what they are looking at. For high-volume pipelines this wastes bandwidth and causes browser performance issues. |
| How | In server.js, listen for a 'set-filter' socket event with payload {app, level, keyword}. Store the filter on the socket object (socket.logFilter = filter). In the setupTail onLog callback, only emit to a client if its logFilter matches the incoming entry (or if no filter is set). Emit a 'filter-applied' acknowledgment back to the client. |
| Files | backend/server.js |
| Needs | HIGH |
| 0D9488 |  |

Member 3 — Aasiya Ankali (23510020) Frontend & UI Engineer · User Interface & Visualization

Aasiya owns the React dashboard — the terminal-style interface developers actually use. She connects to Socket.io, manages the live log buffer, and implements all the features described in the synopsis: live tail, severity filtering, keyword search, color coding, and log download.

## Core Responsibilities

- Build React + Tailwind terminal-style dark dashboard

- Connect to Socket.io server and maintain 1000-entry live log buffer

- Render live log stream with auto-scroll and pause-on-hover

- Color-code log rows by severity: DEBUG/INFO/WARN/ERROR

- Filter by severity level (toggle pills) and by app name (dropdown)

- Keyword search that filters the current visible buffer

- Log download button wired to the backend /api/logs/download endpoint

- Stats bar showing live severity counts and connection status

## Task Breakdown

| #3.1 | React + Vite scaffold with Socket.io client hook |
| --- | --- |
| Why | The entire frontend is built on top of the Socket.io connection and the log buffer. This hook is the foundation every component depends on. |
| How | npm create vite@latest frontend -- --template react. Install tailwindcss, socket.io-client. Create src/hooks/useLogSocket.js: connects to backend Socket.io, listens for new-log events, maintains a logs useState array capped at 1000 entries (slice oldest when exceeded). Return {logs, connected, clearLogs, setFilter}. The setFilter function emits a set-filter socket event to the server. |
| Files | frontend/src/hooks/useLogSocket.js (new) · frontend/package.json · frontend/src/App.jsx |
| CRITICAL |  |

| #3.2 | LogEntry component with severity color coding |
| --- | --- |
| Why | The synopsis specifies color-coding by severity as a core UI feature. A well-styled terminal line makes the dashboard scannable at a glance — developers can spot an ERROR in a stream of INFO logs in under a second. |
| How | Create src/components/LogEntry.jsx. Receives one log object. Renders a terminal-style line: timestamp (gray, fixed-width) + LEVEL badge (bold, colored) + [app] (purple) + message (light gray). Tailwind severity colors: DEBUG=text-gray-500, INFO=text-blue-400, WARN=text-yellow-400, ERROR=text-red-400 with bg-red-950 row. Truncate messages > 300 chars; show full text on hover via title attribute. |
| Files | frontend/src/components/LogEntry.jsx (new) |
| CRITICAL |  |

| #3.3 | LogViewer with auto-scroll and pause-on-hover |
| --- | --- |
| Why | The 'Live Tail' mode is the primary feature of the dashboard. Auto-scroll keeps the latest log visible at all times; pause-on-hover lets developers read without it scrolling away mid-read. |
| How | Create src/components/LogViewer.jsx. Renders filtered logs as a list of LogEntry components in a scrollable div (overflow-y: auto, max-h-screen). useEffect + useRef scrolls to the bottom on every logs update. onMouseEnter pauses auto-scroll (set paused=true), onMouseLeave resumes. When paused, show a 'Paused — hover to resume' badge at the bottom of the viewport. |
| Files | frontend/src/components/LogViewer.jsx (new) · frontend/src/App.jsx |
| Needs | Task 3.2 (LogEntry) must exist |
| CRITICAL |  |

| #3.4 | FilterBar — severity pills, app selector, keyword search |
| --- | --- |
| Why | The synopsis use-case diagram lists Filter by Severity and Search by Keyword as two separate primary use cases. Both must work live against the incoming stream. |
| How | Create src/components/FilterBar.jsx. Severity pills: ALL / DEBUG / INFO / WARN / ERROR — clicking sets activeLevel state in App.jsx. App dropdown: derived from unique app values in the logs buffer. Keyword input: filters messages containing the string (case-insensitive). All three filters are ANDed. Pass active filter to the Socket.io hook's setFilter to also apply server-side. |
| Files | frontend/src/components/FilterBar.jsx (new) · frontend/src/App.jsx |
| Needs | HIGH |
| 2563EB |  |

| #3.5 | Log download button |
| --- | --- |
| Why | Explicitly listed in the synopsis use-case diagram. Users should be able to export exactly what they see in the current filtered view as a .log or .txt file. |
| How | In the dashboard header, add a Download Logs button. On click, build a URL: /api/logs/download?app=<app>&level=<level>&keyword=<keyword> using current filter state. Trigger a file download by creating a temporary <a> element with the href set to this URL and the download attribute set to logs.log, then clicking it programmatically. Remove the element after click. |
| Files | frontend/src/App.jsx |
| Needs | HIGH |
| 2563EB |  |

| #3.6 | StatsBar with live severity counts and connection status |
| --- | --- |
| Why | A stats bar showing real-time counts per severity level (DEBUG 12 · INFO 450 · WARN 8 · ERROR 3) gives an at-a-glance health summary. The connection indicator shows developers if the stream is live or disconnected. |
| How | Create src/components/StatsBar.jsx. Compute levelCounts from the full logs buffer (not filtered). Display as colored pills matching LogEntry colors. Add a connection dot (green pulsing if connected, red if not). Add a 'Clear' button that calls clearLogs from the hook. Place the StatsBar above the FilterBar in the layout. |
| Files | frontend/src/components/StatsBar.jsx (new) · frontend/src/App.jsx |
| Needs | HIGH |
| 2563EB |  |

# 5.  Week-by-Week Build Plan

Eight-week schedule aligned to the synopsis Gantt chart, with specific deliverables per member.

| Week | Member 1 — DevOps | Member 2 — Backend | Member 3 — Frontend |
| --- | --- | --- | --- |
| Week 1 | Docker Compose scaffold, Loki container running on :3100 | Express scaffold, /health route, package.json dependencies | React + Vite scaffold, Tailwind configured |
| Week 2 | Loki config.yml tuned, /ready passing, local storage verified | lokiService.queryLogs() parsing Loki response format | useLogSocket hook, mock log rendering in browser |
| Week 3 | 3 dummy apps writing logs to bind-mounted volumes | Loki tail WebSocket connected, new-log emit working | LogEntry component with all 4 severity colors |
| Week 4 | Promtail scraping all 3 apps, labels visible in Loki | Socket.io filter event handling implemented | LogViewer with auto-scroll + pause-on-hover |
| Week 5 | End-to-end pipeline validated, infra-notes.md written | Download endpoint returning valid .log file | FilterBar: severity pills + app dropdown + keyword input |
| Week 6 | Load test: all 3 apps flooding, no log drops in Loki | Server-side filter reducing emit count, reconnect logic | StatsBar live counts + download button wired |
| Week 7 | Docker resource limits on all services, health checks | Full integration test with live data from all 3 apps | Responsive layout, error states, empty states |
| Week 8 | Final docker-compose.yml cleanup, README, deploy docs | API + socket event documentation | Final UI polish, cross-browser test, demo prep |

# 6.  Integration Checkpoints

Three joint checkpoints. All three members must be present. The team does not proceed to the next phase until gate criteria are verified together.

## Checkpoint 1  —  End of Week 2  (Foundation ready)

| Member 1 — DevOps | Member 2 — Backend | Member 3 — Frontend | Gate |
| --- | --- | --- | --- |
| Loki on :3100, curl /ready = ready | Express on :4000, /health = 200 OK | React app renders in browser on :5173 |
| Promtail config written, no errors | queryLogs() returns Loki JSON without error | useLogSocket connects, no console errors |
| Gate: Loki stores logs | Gate: backend queries Loki | Gate: UI loads and Socket.io connects |

## Checkpoint 2  —  End of Week 4  (Live stream working)

| Member 1 — DevOps | Member 2 — Backend | Member 3 — Frontend | Gate |
| --- | --- | --- | --- |
| All 3 app labels queryable in Loki | Tail WS open, new-log events firing in server console | Logs rendering live in browser in real time |
| Promtail scraping all 3 apps | set-filter event reduces server emit volume | Auto-scroll and pause-on-hover both working |
| Gate: new log → visible in Loki | Gate: Loki event → socket in < 500ms | Gate: browser shows live stream |

## Checkpoint 3  —  End of Week 6  (Full feature parity)

| Member 1 — DevOps | Member 2 — Backend | Member 3 — Frontend | Gate |
| --- | --- | --- | --- |
| Load test complete, pipeline stable | Download endpoint tested with Postman | FilterBar + StatsBar working on live data |
| All 3 app types flowing through stack | 5+ simultaneous Socket.io clients handled | Download button exports correct filtered content |
| Gate: full stack docker compose up | Gate: all routes tested | Gate: demo-ready UI |

# 7.  Repository Structure

| apps/json-logger/ | Node.js app — writes structured JSON logs |
| --- | --- |
| apps/syslog-logger/ | Node.js app — writes RFC 3164 syslog-format logs |
| apps/text-logger/ | Node.js app — writes plain-text logs |
| config/loki-config.yml | Grafana Loki config (storage, retention, auth) |
| config/promtail-config.yml | Promtail scrape rules and pipeline stages |
| backend/server.js | Express + Socket.io server entry point |
| backend/services/lokiService.js | Loki query + tail WebSocket logic |
| backend/.env.example | Environment variable template |
| frontend/src/hooks/useLogSocket.js | Socket.io client hook with 1000-entry log buffer |
| frontend/src/components/LogEntry.jsx | Single color-coded terminal log line |
| frontend/src/components/LogViewer.jsx | Live scrolling log list with auto-scroll |
| frontend/src/components/FilterBar.jsx | Severity pills, app selector, keyword search |
| frontend/src/components/StatsBar.jsx | Live counts by severity + connection indicator |
| docker-compose.yml | Full stack: Loki + Promtail + apps + backend + frontend |
| docs/infra-notes.md | LogQL query reference and Loki API notes |

# 8.  Quick Command Reference

| Start full stack | docker compose up --build |
| --- | --- |
| Start background | docker compose up -d --build |
| Check Loki health | curl http://localhost:3100/ready |
| Query all logs in Loki | curl 'http://localhost:3100/loki/api/v1/query?query={job="logstream"}' |
| View backend logs | docker compose logs -f backend |
| Run backend only | cd backend && npm install && node server.js |
| Run frontend only | cd frontend && npm install && npm run dev |
| Stop stack | docker compose down |
| Stop + remove volumes | docker compose down -v |

LogStream Build Plan · Walchand College of Engineering, Sangli · Mini-Project-2 (7VSCS346) · 2025-26